## Sheet1
Milestones | Tasks | Deliverables | Staff | Time | Av. Rate | Budget
1: Initial Vulnerability Data Set and PoC Detectors | 1.1 Analyze 10+ audited Substrate pallets, runtime code and node code, preparing a repository with annotated versions of both their vulnerable and fixed states. These annotations will highlight the vulnerabilities, their locations within the code, and their classification. | Data Set. An open-source GitHub repository containing annotated Substrate pallets, runtime code and node code, accompanied by a detailed document listing vulnerability classes and their locations within the code. The dataset will also be uploaded toto Hugging Face data sets. | 1 Project Manager (PM) 80h 1 Technical Leader (TL) 160h 1 Security Consultant (Senior Substrate Auditor) 40h 2 Developers (Rust / Substrate) 320h 1 Developer Relations (DevRel) 80h FTEs: 4.25 / 680 hours | 4 weeks | U$55/h | U$D38,000.-
1.2 Compile a list of top/relevant vulnerabilities specific to Substrate pallets, runtime and node code, using audit reports and other publicly available references in the ecosystem ecosystem. (e.g., this blogpost).
| 1.3 Identify security issues that can be effectively addressed with static analysis detectors. | Proof-of-concept version of the detectors. Building on our experience with Scout for ink! and Soroban, we aim to detect 4 vulnerability classes. The tool will be delivered as source code in the repository.
1.4 Adapt existing static analyzer detectors for Rust and ink! (as outlined in Context of the Proposal), currently integrated into Scout, to detect the identified security issues within Substrate pallets, runtime code and node code.
2. Extended Vulnerability Data Set and Prototype Detectors with Precision and Recal | 2.1 Extend the Data Set of vulnerable-projects repository with more annotated pallets, runtimes, and node code (a second set analyzing at least 10 additional pallets/runtimes/nodes). | Extended Data Set. Extended repository of vulnerable pallets, also extending list of vulnerabilities. Updated Hugging Face data set. | 1 Project Manager (PM) 80h 1 Technical Leader (TL) 160h 1 Security Consultant (Senior Substrate Auditor) 40h 2 Developers (Rust / Substrate) 320h 1 Developer Relations (DevRel) 80h FTEs: 4.25 / 680 hours | 4 weeks | U$55/h | U$D38,000.-
2.2 Extend the list of security issues in Substrate and associated test cases by analyzing the second set of audited pallets/runtimes/nodes.
| 2.3 Develop new static analysis detectors for issues identified in the first and current milestone. | Prototype version of the detectors. Given our experience developing Scout for ink! and Soroban we aim to include detection of at least 5 new issue classes. Delivered as source code in the repository.
| 2.4 Create a framework for running analysis tools, similar to SmartBugs but for Rust, to structure the subsequent precision and recall efforts on all detectors built. This framework should run a process that receives a bug detection tool (our static analyzer), a set of audited substrate projects annotated with vulnerabilities, and produces a report. This report shall include: what are the vulnerabilities that were detected, what detections were false positives, and what are the undetected vulnerabilities. | Open Source Framework, for running analysis tools on Rust code, publicly available on CoinFabrik’s GitHub repository.
| 2.5 Analyze precision and recall of static analysis detectors, using the framework developed against the Data Set of audited Substrate projects with annotated vulnerabilities, to find what (problematic) vulnerability classes need better detection. | Detector’s evaluation report on benchmark Data Set. List of suggested vulnerability classes that appear as false negatives in the report, or have a high rate of false positives. (See an example of the evaluation report for Scout for Soroban)
3. Prototype Tool Integration with CLI, VSCode, and CI/CD, Documentation | 3.1 Integrate and Test the Prototype Tool: Implement the following features: Command Line Interface (CLI): Enable various output report formats (HTML, Markdown, SARIF, JSON) and provide detector filter options. VSCode Extension: Display hover error indicators and allow users to enable/disable detectors using inline macros. CI/CD Scout GitHub Action: Make Scout action available on the GitHub Marketplace to seamlessly integrate the tool into development pipelines, providing markdown reports in GitHub Issues and Pull Requests. | A prototype tool that integrates built detectors with a CLI, a VSCode extension, and a CI/CD GitHub Action. (See existing VSCode extension and GitHub Action for ink! and Soroban) | 1 Project Manager (PM) 80h 1 Technical Leader (TL) 160h 1 Security Consultant (Senior Substrate Auditor) 40h 2 Developers (Rust / Substrate) 320h 1 Developer Relations (DevRel) 80h FTEs: 4.25 / 680 hours | 4 weeks | U$55/h | U$D38,000.-
| 3.2 Develop and improve detectors. Address problematic issues identified in Milestone 2. | Additional or improved detectors for problematic issues identified in Milestone 2. Given our experience developing and improving Scout for ink! and Soroban, we aim to improve or further develop 3 detectors. Comprehensive integration tests for all detectors and features.
| 3.3 Document issue classes and associated detectors. | A Documentation Site (using Docusaurus or GitBook) detailing tool usage and an initial set of detectors, including nine documented detectors developed in Milestones 1 and 2. (See the documentation pages for Scout on ink! and Soroban) A public project GitHub repository and website, along with an alpha tool release for selected projects and users.
4. Final Precision and Recall Evaluation & Full Tool Release | 4.1 Conduct final precision and recall evaluation for detectors using the framework developed in Milestone 2 against Data Set of audited Substrate projects with annotated vulnerabilities, to find what (problematic) remaining vulnerability classes need better detection. | Final precision and recall evaluation report. Responsible disclosure of any sensible findings to their corresponding projects.. | 1 Project Manager (PM) 80h 1 Technical Leader (TL) 160h 1 Security Consultant (Senior Substrate Auditor) 40h 2 Developers (Rust / Substrate) 320h 1 Developer Relations (DevRel) 80h FTEs: 4.25 / 680 hours | 4 weeks | U$55/h | U$D38,000.-
| 4.2 Final detector improvements based on precision and recall evaluation. | Fully integrated tool with CLI, VSCode Extension, and/or CI/CD GitHub Action. Public release of the tool with full documentation, publicly available on documentation sites (Docusaurus or GitBook)(See documentation examples here and here).
4.3 Document remaining detectors and issue classes.
| 4.4 Create video tutorials on tool usage and issue classes. | Video tutorials on how to use the tool, along with one video tutorial for each issue detected by the tool. Given our experience developing Scout for ink! and Soroban, we aim to publish between 10 and 15 video tutorials on CoinFabrik’s YouTube channel. (See Scout video tutorials for other blockchain here).
| 4.5 Create Release webinar and social media comms. | Release Webinar. Posts on CoinFabrik’s social media.
[5 empty] | TOTAL | U$152,000.-